PROJECT REPORT

CUSTOMER SUPPORT TICKET PRIORITY PREDICTION AND AUTOMATED ASSIGNMENT SYSTEM USING AGENTFORCE

Phase 6: Project Planning

# 1. Introduction

Project planning explains how the work is organized, who does what and in which order. The project follows the Agile method with short sprints. Work is divided into Epics, then User Stories, then Story Points, and progress is followed using sprint velocity and a burndown chart.

# 2. Planning Approach

- Agile methodology with work carried out in sprints.

- Epics are broken into stories, and stories are estimated in story points.

- Velocity (story points completed per sprint) is used for estimation.

- Six sprints, each lasting one week (6 working days).

# 3. Team Roles

Replace the member labels below with the real names of your team members.

| Team member | Responsibility |
| --- | --- |
| Member 1 | Environment setup and Agentforce subagent configuration (Sprints 1 and 4) |
| Member 2 | Data modeling and task and assignment automation (Sprints 2 and 4) |
| Member 3 | Account and Contact relationships and SLA management (Sprints 2 and 5) |
| Member 4 | Flow logic, priority classification and conversational support (Sprints 3 and 6) |

# 4. Product Backlog

| Sprint | Epic | Story | User story / task | Pts | Priority | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Developer setup | USN-1 | As a system administrator, I want to configure the Salesforce environment for Support Ticket Intelligence so that the automation can be developed | 3 | High | Member 1 |
| 2 | Data modeling | USN-2 | As an admin, I want to create the Support Ticket Intelligence object with the required fields and relationships so that ticket information is stored in an organized way | 5 | High | Member 2 |
| 2 | Data modeling | USN-3 | As a support user, I want tickets linked to Accounts and Contacts so that the latest customer ticket can be identified | 3 | High | Member 3 |
| 3 | Automation | USN-4 | As a support agent, I want an Auto-Launched Flow to fetch the latest ticket and analyze its description so that priority is decided automatically | 5 | High | Member 4 |
| 3 | Automation | USN-5 | As a support agent, I want tickets classified as High, Medium or Low so that critical issues get attention first | 5 | High | Member 4 |
| 4 | Agentforce and automation | USN-6 | As an AI agent, I want to analyze ticket details and trigger the backend Flow so that manual prioritization is reduced | 8 | High | Member 1 |
| 4 | Task and assignment | USN-7 | As a support manager, I want High tickets to create an urgent task and assign the support level so that critical tickets are handled quickly | 5 | High | Member 2 |
| 5 | SLA management | USN-8 | As a support manager, I want the system to check SLA breach risk for older unresolved tickets | 5 | Medium | Member 3 |
| 6 | Conversational support | USN-9 | As a support user, I want to give an Account Name to Agentforce and receive the ticket Id, priority, assigned agent and action message | 5 | Medium | Member 4 |

# 5. Sprint Schedule and Estimation

| Sprint | Duration | Timeline | Focus | Story points |
| --- | --- | --- | --- | --- |
| Sprint 1 | 6 days | Week 1 | Developer org and environment setup | 3 |
| Sprint 2 | 6 days | Week 2 | Custom object, fields, Account and Contact links | 8 |
| Sprint 3 | 6 days | Week 3 | Auto-Launched Flow and priority classification | 10 |
| Sprint 4 | 6 days | Week 4 | Agentforce subagent, Flow action, urgent task and assignment | 13 |
| Sprint 5 | 6 days | Week 5 | SLA risk check | 5 |
| Sprint 6 | 6 days | Week 6 | Conversational output, testing and documentation | 5 |
| Total |  | 6 weeks |  | 44 |

# 6. Velocity Calculation

Total story points = 3 + 8 + 10 + 13 + 5 + 5 = 44. Number of sprints = 6. Average velocity = 44 / 6 = about 7.3 story points per sprint.

The average velocity can be used to estimate remaining work after any sprint. For instance, if 8 points are finished in Sprint 2, the remaining 33 points need roughly 4 to 5 more sprints, which agrees with the plan.

# 7. Project Tracker and Burndown Chart

| Sprint | Points planned | Points completed | Remaining after sprint |
| --- | --- | --- | --- |
| Sprint 1 | 3 | 3 | 41 |
| Sprint 2 | 8 | 8 | 33 |
| Sprint 3 | 10 | 10 | 23 |
| Sprint 4 | 13 | 13 | 10 |
| Sprint 5 | 5 | 5 | 5 |
| Sprint 6 | 5 | 5 | 0 |

Figure 1: Sprint burndown chart

# 8. Milestones

| Milestone | Description | Deliverable |
| --- | --- | --- |
| M1 | Salesforce account created and activated | Developer org ready |
| M2 | Data management: custom object and fields | Support Ticket Intelligence object |
| M3 | Flow logic completed | Support_Ticket_Intellegence flow (active) |
| M4 | Agentforce configuration | Subagent and Flow action |
| M5 | Testing and documentation | Test results and project report |

# 9. Risk Management

| Risk | Impact | Response |
| --- | --- | --- |
| Agentforce not enabled in the org | High | Enable it through Salesforce Go in Sprint 1 |
| Errors in the Flow logic | Medium | Debug with test records before connecting to the agent |
| Growth of scope | Medium | Keep extra ideas as future scope and follow the backlog |
| Shortage of time | Medium | Move Medium-priority stories to the next sprint |

# 10. Testing Plan

- Unit testing of the Flow using sample tickets with High, Medium and Low descriptions.

- Integration testing of the Agentforce action with the Flow in Conversation Preview.

- Verification that a task is created and assigned for High-priority tickets.